**security control system**

|  |  |  |
| --- | --- | --- |
| 4 | B | 6 |
| 0 | Assign  team |  |
| 4 | 2 | 6 |

|  |  |  |
| --- | --- | --- |
| 14 | H | 18 |
| 0 | Integrate  Systems |  |
| 14 | 4 | 18 |

|  |  |  |
| --- | --- | --- |
| 6 | D | 10 |
| 0 | Code  Software |  |
| 6 | 4 | 10 |

|  |  |  |
| --- | --- | --- |
| 10 | G | 14 |
| 0 | Test  Software |  |
| 10 | 4 | 14 |

Activity Description Preceding Activity

A Define Requirement None

1. Assign team A
2. Design Hardware A
3. Code Software B E Build& test Hardware C

F Develop Patent Request C G Test Software D

H Integrate Systems E,F,G

|  |  |  |
| --- | --- | --- |
| 10 | E | 14 |
| 4 | Build& test  Hardware |  |
| 6 | 4 | 10 |

|  |  |  |
| --- | --- | --- |
| 0 | A | 4 |
| 0 | Define  Requirement |  |
| 0 | 4 | 4 |

|  |  |  |
| --- | --- | --- |
| 8 | C | 10 |
| 4 | Design  Hardware |  |
| 4 | 2 | 6 |

|  |  |  |
| --- | --- | --- |
| 12 | F | 14 |
| 6 | Develop Patent  Request |  |
| 6 | 2 | 8 |

Team members:

احمد عبد الظاهر احمد صبره

ابرام رسمي عياد زاخر

ابانوب مرزق شنوده خلة

احمد السيد فاروق

احلام رضا عبد المنعم

ابتسام سيد محفوظ سيد